## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Mutheiswari | 2024-11-11 | Denied permission for Web scrapping by kaggle. | 1 | Shreyash | Standards | Kaggle API used for downloading the datasets. | 2024-11-11 | Closed | Downloaded the dataset by installing kaggle instead of web scrapping because of security norms of kaggle.
2 | Varsha | 2024-11-18 | Executional Errors while doing TF-IDF vectorization. | 1 | Shreyash | Logical | Debugging done. | 2024-11-18 | Closed | Executional Errors.
3 | Shreyash | 2024-11-27 | Unconsitent Model performance. | 2 | Shreyash | Standards | used Random state 42 for consistent results | 2024-11-28 | Closed
4 | Shrihari R | 2024-11-30 | Executional Errors while XGBoost Model Building. | 2 | Shrihari R | Logical | Used label encoder to fix the Error. | 2024-11-01 | Closed
5 | Shreyash | 2024-12-03 | Model pipeline unexecutional because of absence of label encoder. | 2 | Shreyash | Logical | Initialized label encoder for encoding dataset before intializing Model pipeline. | 2024-12-05 | Closed | Optimized Model pipeline code is now executional.
6 | Vishnu | 2024-12-05 | Error oucurence in ROC code. | 2 | Shreyash | Logical | Resolved issue using identifying indivisual model. | 2024-12-05 | Closed | Reason for the error was because of alteration in Model Building pipeline code.
7 | Vishnu | 2024-12-11 | Selecting Hyperparameters for the Logistic Regression and Random Forest | 3 | Vishnu | Standards | researched on what are the best parameters to be used | 2024-12-11 | Closed
8 | Shreyash | 2024-12-12 | Selecting Hyperparameters for the Xg boost | 3 | Shreyash | Logical | researched on what are the best parameters to be used | 2024-12-12 | Closed
9 | Nandini | 2024-12-14 | Selecting Hyperparameters for the Decision tree | 3 | Nandini | Logical | researched on what are the best parameters to be used | 2024-12-14 | Closed
10 | Shrihari R | 2024-12-14 | Selecting Hyperparameters for the Ada boost | 3 | Shrihari R | Logical | researched on what are the best parameters to be used | 2024-12-14 | Closed
11 | Shreyash | 2024-12-16 | Error oucurence in Parameters assignment for Xg Boost and Ada Boost | 3 | Shreyash | Logical | Solved the errors by refering module documentation | 2024-12-16 | Closed
12 | Vishnu | 2024-12-16 | Error oucurence in Parameters assignment | 3 | Vishnu | Logical | Solved the errors by refering module documentation | 2024-12-16 | Closed
13 | Vishnu | 2024-12-23 | Error while testing the model | 4 | Vishnu | Logical | Solved the errors by refering module documentation | 2024-12-21 | Closed
14 | Shrihari R | 2024-12-24 | Error occurance while selecting the framework for deploying the model | 4 | Shrihari R | Logical | Solved the errors by refering module documentation | 2024-12-24 | Closed
15 | Nandini | 2024-12-24 | Error while initiating the deployment of model | 4 | Nandini | Logical | Solved the errors by refering module documentation | 2024-12-26 | Closed
16 | Shreyash | 2024-12-27 | Error while final Deployment of model | 4 | Shreyash | Logical | Solved the errors by refering module documentation | 2024-12-27 | Closed